## Committed (TB1)
ConnectRVA 2045 - Cost Constrained List of Regional Projects - Time Band 1 (FY22-FY27) Committed
UPC | Description | Cost (Thousands) | Prev | FY22 | FY23-FY27 | Time-Band 1 Total | Balance
110394 | #HB2.FY17 RTE 64 - MAJOR WIDENING GARVEE DEBT SERVICE | 77238 | 18080 | 4925 | 9849 | 14774 | 44385
111984 | #SMART18 - I-95 AUXLANES B/W RTE.288/RTE.10-GARVEE DEBT SERV | 34490 | 1066 | 813 | 4002 | 4815 | 28609
111981 | #SMART18 - BBC PH 1-BAILEY BR, BRAD MCNEER-GARVEE DEBT SERV | 29203 | 0 | 557 | 3464 | 4021 | 25183
112974 | RTE 668 (WOOLRIDGE ROAD, RT 288-OLD HUNDRED ROAD) EXTENSION | 47000 | 15300 | 800 | 8432 | 9232 | 22468
110393 | #HB2.FY17 RT 10 (BERM TRI TO MEADOWV) GARVEE DEBT SERVICE | 32546 | 4271 | 2113 | 4227 | 6340 | 21934
101492 | RICHMOND REGION-WIDE TRAFFIC/OPERATIONS IMPROVEMENTS | 34540 | 555 | 0 | 20656 | 20656 | 13329
109310 | #HB2.FY17 SHOCKOE VALLEY ST IMPROVEMENT | 39250 | 17846 | 2577 | 7620 | 10197 | 11207
118470 | W BROAD ST PEDESTRIAN AND TRANSIT IMPROVEMENTS - GLENSIDE DR | 11272 | 0 | 0 | 2195 | 2195 | 9077
118597 | W BROAD ST INTERSECTION IMPROVEMENTS AT DOMINION AND COX | 13952 | 379 | 0 | 8327 | 8327 | 5246
50529 | RTE 9999 (THREE CHOPT ROAD) WIDEN TO 4 LANES | 30819 | 24654 | 0 | 962 | 962 | 5203
107088 | RTE 636 - NASH ROAD EXTENSION | 30052 | 8122 | 878 | 16216 | 17094 | 4836
118153 | BROOK ROAD & HILLIARD ROAD TRAIL | 4757 | 0 | 0 | 2196 | 2196 | 2561
118146 | ROUTE 1 (HOLIDAY LANE - WILLIS ROAD) SHARED-USE PATH | 4370 | 0 | 0 | 1832 | 1832 | 2538
113323 | RTE 632 (FAIRGROUND ROAD) EXTENSION | 6101 | 1500 | 563 | 1734 | 2297 | 2303
101034 | #HB2.FY17 RTE 6 PATTERSON AVE AT PARHAM RD INTERSECTION | 14000 | 9358 | 4210 | 0 | 4210 | 432
117049 | S. LABURNUM/ROUTE 5 INTERSECTION IMPROVEMENTS | 290 | 0 | 0 | 228 | 228 | 61
109260 | POLE GREEN RD WIDENING | 20000 | 5764 | 1904 | 12302 | 14206 | 29
T25026 | #SMART22 - ASHCAKE ROAD PEDESTRIAN IMPROVEMENTS | 4622 | 0 | 1500 | 3102 | 4602 | 20
111713 | #SMART18 - BBC PH 1 - BAILEY BR CONN., BRAD MCNEER CONN. | 22960 | 2069 | 13000 | 7891 | 20891 | 0
T25110 | #SMART22 - ROUTE 1 PHASE II IMPROVEMENTS | 13242 | 0 | 5819 | 7423 | 13242 | 0
13551 | #SMART18 - RTE 360 WIDENING | 23953 | 13457 | 5207 | 5288 | 10495 | 0
109320 | #HB2.FY17 SB I95 BELVIDERE ST INTERCHANGE SAFETY IMPROVEMENT | 10229 | 3341 | 5162 | 1727 | 6889 | 0
107083 | RTE 621 (WINTERPOCK, 360-ROYAL BIRKDALE) - MAJOR WIDENING | 21478 | 7667 | 4806 | 9005 | 13811 | 0
111467 | #SMART18 - SB RT 288 TO WB US 360 WB OFF-RAMP, US360 PNRLOT | 14562 | 9831 | 4730 | 0 | 4730 | 0
104889 | RT 10 (WHITEPINE TO FRITH) WIDENING | 15171 | 9908 | 3263 | 2000 | 5263 | 0
111716 | #SMART18 - RICHMOND-HENRICO TURNPIKE -- SOUTH SGMT | 18642 | 10392 | 3216 | 5034 | 8250 | 0
118091 | LAKESIDE COMMUNITY TRAIL PHASE 2 | 2971 | 1462 | 1509 | 0 | 1509 | 0
112042 | ROUTE 1 IMPROVEMENTS: ASHCAKE RD TO ARBOR OAK DR | 11312 | 3648 | 1295 | 6369 | 7664 | 0
115815 | I-64 EXPRESS BARGE SERVICE EXPANSION | 3000 | 0 | 920 | 2080 | 3000 | 0
113832 | RICHMOND MARINE TERMINAL (RMT) GATE IMPR. & NEW DROP-OFF LOT | 3379 | 2526 | 852 | 0 | 852 | 0
111465 | #SMART18 - I-95/I-64 OVERLAP: EMERGENCY PULL-OFFS | 2780 | 2000 | 780 | 0 | 780 | 0
109322 | #HB2.FY17 RTE 95 - IMPROVE INTERCHANGE AT RTE 10 | 11426 | 9945 | 701 | 781 | 1482 | 0
118065 | LAKESIDE COMMUNITY TRAIL PHASE 1 | 1824 | 1311 | 513 | 0 | 513 | 0
104890 | RTE 360 E (LONAS PKWY TO CASTLE ROCK RD) - WIDENING | 7034 | 6840 | 194 | 0 | 194 | 0
115415 | #SMART20 - RT 1 (FALLING CK. WAYSIDE - FOOD LION) BIKE/PED | 3331 | 487 | 150 | 2694 | 2844 | 0
110910 | #SMART18 - PARHAM RD PEDESTRIAN & TRANSIT STOP IMPROVEMENTS | 726 | 667 | 59 | 0 | 59 | 0
T25107 | #SMART22 - BROAD STREET STREETSCAPE W/ PULSE BRT EXPANSION | 26803 | 0 | 0 | 26803 | 26803 | 0
T25106 | #SMART22 - NINE MILE RD MULTIMODAL MOBILITY & SAFETY IMPROVE | 14116 | 0 | 0 | 14116 | 14116 | 0
T25027 | #SMART22 - WILLIAMSBURG RD PEDESTRIAN & TRANSIT IMPROVEMENTS | 15440 | 0 | 0 | 15440 | 15440 | 0
115414 | #SMART20 - JUDE'S FERRY ROAD & ROUTE 60 | 2472 | 347 | 0 | 2125 | 2125 | 0
106296 | RTE 155 - CONSTRUCT TRAIL (PE ONLY) | 400 | 0 | 0 | 400 | 400 | 0
T25108 | #SMART22 - ARTICULATED VEHICLES FOR BUS RAPID TRANSIT EXPANS | 3356 | 0 | 0 | 3356 | 3356 | 0
111637 | #SMART18 - BROAD ST PEDESTRIAN & TRANSIT STOP IMPROVEMENTS | 1367 | 536 | 0 | 831 | 831 | 0
115417 | #SMART20 - W BROAD ST PEDESTRIAN AND TRANSIT IMPROVEMENTS | 10857 | 1153 | 0 | 9704 | 9704 | 0
115555 | #SMART20 - SCOTT'S ADD BRT STATION PED SAFETY/STREETSCAPE | 1612 | 0 | 0 | 1612 | 1612 | 0
115195 | ATLEE STATION RD WIDENING | 31529 | 4106 | 0 | 27423 | 27423 | 0
T25168 | #SMART22 - SLIDING HILL ROAD/PEAKS ROAD ROUNDABOUT | 7501 | 0 | 0 | 7501 | 7501 | 0
115411 | #SMART20 - N LABURNUM AVE PED AND TRANSIT IMPROVEMENTS | 3054 | 365 | 0 | 2689 | 2689 | 0
T25109 | #SMART22 - JAMES RIVER BRANCH - RAIL TO TRAIL GREENWAY | 14303 | 0 | 0 | 14303 | 14303 | 0
T24908 | #SMART22 - GILLIES CREEK GREENWAY | 3759 | 0 | 0 | 3759 | 3759 | 0
115410 | #SMART20 - RIVERFRONT/ORLEANS BRT STATION PED SAFETY/STREETS | 2057 | 0 | 0 | 2057 | 2057 | 0
115416 | #SMART20 SHOCKOE BOTTOM BRT STATION PED SAFETY/STREETSCAPE | 4900 | 0 | 0 | 4900 | 4900 | 0
108649 | RTE 5 (MAIN STREET) - NEW ROAD | 2800 | 599 | 1136 | 1067 | 2203 | -2
109321 | #HB2.FY17 RTE 95 - IMPROVE INTERCHANGE AT MAURY ST | 7905 | 7757 | 191 | 0 | 191 | -43
104148 | SADLER RD - RECONSTRUCTION | 27107 | 17587 | 0 | 10103 | 10103 | -583
111466 | #SMART18 - I-95 AUX LANES (NB & SB) B/W RTE. 288 & RTE. 10 | 27912 | 7199 | 10000 | 11571 | 21571 | -858
104281 | DEEPWATER TERMINAL RD - EXTEND EXISTING ROADWAY | 5458 | 2676 | 3501 | 1234 | 4735 | -1953
T25115 | #SMART22 - POWHITE NB AT CHIPPENHAM CAPACITY AND SAFETY IMPR | 17169 | 0 | 0 | 17169 | 17169 | 0
TBD | Powhite SB at Chippenham Capacity and Safety Improvements | 9436.1807 | 0 | 0 | 9436.1807 | 9436.1807 | 0
TBD | Ashland to Petersburg Trail US 1 Walmsley to Bellemeade | 16171.2644 | 0 | 0 | 16171.2644 | 16171.2644 | 0
TBD | Ashland to Petersburg Trail - Chickahominy River Crossing | 4989.9076 | 0 | 0 | 4989.9076 | 4989.9076 | 0
TBD | A-to-P Trail: Rt. 1 (Falling Creek Ave. - Food Lion) | 12547.0611 | 0 | 0 | 12547.0611 | 12547.0611 | 0
466787.4138
Project also in the ConnectRVA 2045 Universe of Projects

## TB1
ConnectRVA 2045 - Cost Constrained List of Regional Projects - Time Band 1 (FY22-FY27) (Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Inflated Cost | Flexible Funds | Transit Funds | Active Funds | Air Quality Funds | Rank | Time -Band | Staff Notes
215 | FAT-15 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 5B - MM 25.6 to MM 26.6 | Off- Road/On-Road Trail | N/A | 3rd St. | W. Duval St | Richmond | 1189000 | 0 | 0 | 1189000 | 0 | 1 | 1
33 | FHW-33 | I-295 | Construction of a SB auxiliary lane between the existing lane drop on I-295 SB and Chamberlayne Rd (Exit 41) off ramp (0.4mi) | Auxiliary Lane | SB | I-95 Southbound Branch | Chamberlayne Rd (Exit- 41) off ramp | Hanover/Henrico | 585000 | 585000 | 0 | 0 | 0 | 2 | 1
219 | FAT-19 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 6B - MM 30.5 to MM 31.2 | Off- Road/On-Road Trail | N/A | Bellevue Ave | Lakeside Ave | Richmond | 540000 | 0 | 0 | 540000 | 0 | 3 | 1
214 | FAT-14 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 4D - MM 23.9 to MM 24.3 | Off- Road/On-Road Trail | N/A | Semmes Ave | Potterfield Bridge | Richmond | 664000 | 0 | 0 | 664000 | 0 | 4 | 1
267 | FTR-10 | NA | 23rd Street & Franklin Street Neighborhood Transit Center | New Transit Transfer Center | N/A | NA | NA | Richmond | 340000 | 340000 | 0 | 0 | 0 | 5 | 1
210 | FAT-10 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 3E - MM 17.7 to MM 18.6 | Off- Road/On-Road Trail | N/A | US-1 | Walmsley Blvd | Chesterfield | 659000 | 0 | 0 | 659000 | 0 | 6 | 1
201 | FAT-1 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 2B - MM 4.0 to MM 9.4 (Only Portion Within RRTPO) | Off- Road/On-Road Trail | N/A | Brander Bridge Rd | VA- 10/W. Hundred Rd | Chesterfield | 698000 | 0 | 0 | 698000 | 0 | 7 | 1
230 | FAT-30 | Magolia Ridge Dr | Multiuse trail connecting Fall Line to Virginia Center Commons | Off Road Trail | N/A | Brook Rd | Woodman Rd Extended | Henrico | 717000 | 0 | 0 | 717000 | 0 | 8 | 1
225 | FAT-25 | East End Trail/West Creek Trail | Trail through West Creek area of Goochland County | Off Road Trail | N/A | West Creek/Patterson | Wilkes Ridge Pkwy | Goochland | 1285000 | 118085 | 0 | 1166915 | 0 | 9 | 1
212 | FAT-12 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 4B - MM 20.7 to MM 21.8 | Off- Road/On-Road Trail | N/A | Bellemeade Rd | Commerce Rd. | Richmond | 1071000 | 1071000 | 0 | 0 | 0 | 10 | 1
217 | FAT-17 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 5D - MM 27.6 to MM 28.5 | Off- Road/On-Road Trail | N/A | Admiral St | Brookland Pkwy | Richmond | 1583000 | 1583000 | 0 | 0 | 0 | 11 | 1
119 | FHW-119 | US-1 & E Parham Rd | Operational improvements and pedestrian accommodations | Intersection Improvement | NA | NA | NA | Henrico | 1656000 | 1656000 | 0 | 0 | 0 | 12 | 1
232 | FAT-32 | Connector to Stratton Park | Shared Use Path (eventually connecting Stratton Park to Pocahontas State Park) | Off Road Trail | N/A | VA-150 | Jessup Road | Chesterfield | 1766000 | 1766000 | 0 | 0 | 0 | 13 | 1
216 | FAT-16 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 5C - MM 26.6 to MM 27.6 | Off- Road/On-Road Trail | N/A | W. Duval St | Admiral St | Richmond | 3471000 | 3471000 | 0 | 0 | 0 | 14 | 1
248 | FPR-14 | I-64 & VA- 623 (Ashland Rd) | Relocating existing P & R lot with 180 parking spaces | Park & Ride | N/A | NA | NA | Goochland | 1987000 | 1987000 | 0 | 0 | 0 | 15 | 1
208 | FAT-8 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 3D - MM 16.8 to MM 17.7 | Off- Road/On-Road Trail | N/A | Wayside Park/Falling Cr | US-1 | Chesterfield | 1743000 | 1743000 | 0 | 0 | 0 | 16 | 1
83 | FHW-83 | Mill Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Mill Place Dr | Mountain Rd | Henrico | 2760000 | 2760000 | 0 | 0 | 0 | 17 | 1
204 | FAT-4 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 3A - MM 12.9 to MM 13.6 | Off- Road/On-Road Trail | N/A | Galena Ave | Kingsdale Rd | Chesterfield | 1947000 | 1947000 | 0 | 0 | 0 | 18 | 1
35 | FHW-35 | I-295 | Widening of the cross-section between I-295 SB deceleration and Exit 43 (Brook Rd) to a two-lane section (0.5mi) | Interchange Modification | SB | I-295 SB deceleration lane | Exit 43 C | Henrico | 4415000 | 4415000 | 0 | 0 | 0 | 19 | 1
247 | FPR-13 | VA-288 at US-250 | New P & R lot near US 288/US 250 interchange of 100 parking spaces | Park & Ride | N/A | NA | NA | Goochland | 1987000 | 1987000 | 0 | 0 | 0 | 20 | 1
68 | FHW-68 | I-95 & VA-161 | Conversion of SB I-95 off-ramp at VA-161 (Exit 78) to two lanes. Removal of one lane from SB I-95 prior to on-ramp from EB I-64. Merge 3 lanes to 2 before on-ramp from I-64. Convert off-ramp to Boulevard ( VA-161) to 2 lanes (1 choose lane). | Interchange Modification | N/A | N/A | N/A | Richmond | 5850000 | 5850000 | 0 | 0 | 0 | 21 | 1
239 | FPR-5 | I-64/US-60 at Laburnum Rd | New P&R lot of 120 spaces on 0.8 AC parcel | Park & Ride | N/A | NA | NA | Henrico | 3146000 | 3146000 | 0 | 0 | 0 | 22 | 1
218 | FAT-18 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 6A - MM 28.5 to MM 30.5 | Off- Road/On-Road Trail | N/A | Brookland Pkwy | Bellevue Ave | Richmond | 3610000 | 3610000 | 0 | 0 | 0 | 23 | 1
139 | FHW-139 | US-60 & Stavemill Rd | Installation of a second left-turn lane along westbound US-60 | Intersection Improvement | NA | NA | NA | Powhatan | 2567000 | 2567000 | 0 | 0 | 0 | 24 | 1
97 | FHW-97 | Pouncey Tract Rd | Widening with added capacity (0.25 mi) | Road Widening | Both | Henrico Co. Line | Ashland Rd | Hanover | 3311000 | 3311000 | 0 | 0 | 0 | 25 | 1
107 | FHW-107 | S Airport Dr | Widening with added capacity and bike/ped facilities | Road Widening | Both | Audubon Dr | Williamsburg Rd | Henrico | 5519000 | 5519000 | 0 | 0 | 0 | 26 | 1
243 | FPR-9 | Huguenot Rd at Forest Hill Ave | New P&R lot to replace unofficial lot, 130 spaces on 0.9 AC | Park & Ride | N/A | NA | NA | Chesterfield | 3311000 | 3311000 | 0 | 0 | 0 | 27 | 1
240 | FPR-6 | I-295at US-60-Technology Blvd/Elko Rd | New P& R lot of 120 space on 0.8 AC as alternative to Bottoms Bridge P&R expansion which is over-capacity | Park & Ride | N/A | NA | NA | Henrico or New Kent | 3146000 | 3146000 | 0 | 0 | 0 | 29 | 1
245 | FPR-11 | VA- 76/US-60 | New P& R lot | Park & Ride | N/A | NA | NA | Chesterfield | 5519000 | 5519000 | 0 | 0 | 0 | 30 | 1
246 | FPR-12 | VA-76/Jhanke | New P& R lot | Park & Ride | N/A | NA | NA | Chesterfield | 5519000 | 5519000 | 0 | 0 | 0 | 31 | 1
182 | FHW-182 | Woodman Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Hermitage Rd | Hilliard Rd | Henrico | 5519000 | 5519000 | 0 | 0 | 0 | 32 | 1
147 | FHW-147 | VA-150 & Dalebrook Dr | Elimination of On and Off-Ramps | Interchange Modification | SB | N/A | N/A | Chesterfield | 5519000 | 5519000 | 0 | 0 | 0 | 33 | 1
29 | FHW-29 | Hockett Rd | Realignment/Construction of a new road | Road Realignment | Both | Hockett Rd | Broad Street Rd | Goochland | 3699000 | 3699000 | 0 | 0 | 0 | 34 | 1
90 | FHW-90 | Old Hundred Road | Widening with added capacity | Road Widening | Both | US-60 | Mt Hermon Rd | Chesterfield | 6071000 | 6071000 | 0 | 0 | 0 | 36 | 1
30 | FHW-30 | Horsepen Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Three Chopt Rd | Dexter Rd | Henrico | 6181000 | 6181000 | 0 | 0 | 0 | 37 | 1
129 | FHW-129 | US-360 & Broad Rock Blvd | Construction of an alternative intersection with displaced left turns | Intersection Improvement | NA | NA | NA | Richmond | 5519000 | 5519000 | 0 | 0 | 0 | 38 | 1
137 | FHW-137 | US-60 & Dorset Rd | Reconfiguration of the intersection of US- 60 and Dorset Road( VA-622) to a RCUT with two northbound right-turn lanes. | Intersection Improvement | NA | NA | NA | Powhatan | 4084000 | 4084000 | 0 | 0 | 0 | 39 | 1
146 | FHW-146 | VA-150 & Dalebrook Dr | Elimination of On and Off-Ramps | Interchange Modification | NB | N/A | N/A | Chesterfield | 5519000 | 5519000 | 0 | 0 | 0 | 40 | 1
238 | FPR-4 | East End CBD at Pulse Terminus-Rocketts | New P&R lot of 130 spaces on 0.9 AC parcel | Park & Ride | N/A | NA | NA | Henrico or Richmond | 3311000 | 3311000 | 0 | 0 | 0 | 41 | 1
242 | FPR-8 | US-250 at Willow Lawn/Staples Mill (Pulse western terminus) | New P&R lot subject of much site search, 290 spaces on 2.0 AC | Park & Ride | N/A | NA | NA | Henrico | 6623000 | 6623000 | 0 | 0 | 0 | 42 | 1
237 | FPR-3 | Midlothian @ Chippenham | New P&R lot of 270 spaces on 1.9 AC | Park & Ride | N/A | NA | NA | Chesterfield | 8058000 | 8058000 | 0 | 0 | 0 | 43 | 1
221 | FAT-21 | Fall Line / Route 1 | Henrico Fall Line Trail Phase 6: Villa Park | Off- Road/On-Road Trail | N/A | Lakeside Ave | Parham Rd | Henrico | 4636000 | 4636000 | 0 | 0 | 0 | 44 | 1
7 | FHW-7 | Bethlehem Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Libbie Ave | Dickens Rd | Henrico | 7175000 | 7175000 | 0 | 0 | 0 | 45 | 1
70 | FHW-70 | I-95 & VA-54 | Connection SB I-95 off-ramp to Hill Carter Pkwy | Interchange Modification | N/A | N/A | N/A | Ashland | 3863000 | 3863000 | 0 | 0 | 0 | 46 | 1
39 | FHW-39 | I-295 & Creighton Rd | Widening of the NB VA- 288 Off-Ramp to Two Lanes. | Interchange Modification | NB | I-295 NB | Creighton Rd NB | Hanover | 3311000 | 3311000 | 0 | 0 | 0 | 47 | 1
213 | FAT-13 | Fall Line / Route 1 | Richmond Fall Line Trail: Segment 4C - MM 21.8 to MM 23.9 | Off- Road/On-Road Trail | N/A | Commerce Rd | Decatur St | Richmond | 6316000 | 6316000 | 0 | 0 | 0 | 48 | 1
124 | FHW-124 | US-250 & Pouncey Tract Rd | Increase capacity at US-250 & Pouncey Tract Rd intersection with an additional lane | Intersection Improvement | NA | NA | NA | Henrico | 5519000 | 5519000 | 0 | 0 | 0 | 50 | 1
45 | FHW-45 | I-64 | Construction of an auxiliary lane between Exit 185 (US-33) and Exit 186 (I-195) | Auxiliary Lane | WB | Exit 185 | Exit 186 | Henrico/Richmond | 13246000 | 13246000 | 0 | 0 | 0 | 51 | 1
26 | FHW-26 | Dickens Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Staples Mill Rd | Oconto Rd | Henrico | 8831000 | 8831000 | 0 | 0 | 0 | 52 | 1
122 | FHW-122 | US-250 & Glenside Drive | Operational improvements and pedestrian accommodations | Intersection Improvement | N/A | N/A | N/A | Henrico | 5519000 | 5519000 | 0 | 0 | 0 | 53 | 1
203 | FAT-3 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 2D - MM 10.7 to MM 12.9 | Off- Road/On-Road Trail | N/A | Chester Rd | Galena Ave | Chesterfield | 4603000 | 4603000 | 0 | 0 | 0 | 55 | 1
228 | FAT-28 | Nuckols Rd Trail | Multiuse Trail | Off Road Trail | N/A | Springfield Rd | Francistown Rd | Henrico | 4415000 | 4415000 | 0 | 0 | 0 | 57 | 1
169 | FHW-169 | VA-54 | Widening with added capacity | Road Widening | Both | Frances Rd | East Corporate Limits | Ashland | 6093000 | 6093000 | 0 | 0 | 0 | 58 | 1
156 | FHW-156 | VA-161, Brookland Pkwy & Westwood Ave | Construction of a new roundabout in the five legged intersection | Intersection Improvement | NA | NA | NA | Richmond | 8831000 | 8831000 | 0 | 0 | 0 | 59 | 1
244 | FPR-10 | I-64 at I-295 in Short Pump | New P& R lot of 320 spaces on 2.2 AC | Park & Ride | N/A | NA | NA | Henrico | 7727000 | 7727000 | 0 | 0 | 0 | 60 | 1
110 | FHW-110 | Springfield Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Staples Mill Rd | Francistown Rd | Henrico | 8279000 | 8279000 | 0 | 0 | 0 | 61 | 1
150 | FHW-150 | VA-150 & Strathmore Rd | Elimination of On and Off-Ramps | Interchange Modification | NB | N/A | N/A | Chesterfield | 5519000 | 5519000 | 0 | 0 | 0 | 62 | 1
132 | FHW-132 | US-360, Midlothian Turnpike & Clopton St | Construction of a new roundabout in the five legged intersection | Intersection Improvement | NA | NA | NA | Richmond | 8831000 | 8831000 | 0 | 0 | 0 | 63 | 1
224 | FAT-24 | Fall Line / Route 1 | Hanover Fall Line: Segment 7C - MM 37.4 to MM 43.3 | Off- Road/On-Road Trail | N/A | Winfrey Rd (Henrico) | Gwathmey Church Rd | Hanover | 4873000 | 4873000 | 0 | 0 | 0 | 64 | 1
220 | FAT-20 | Fall Line / Route 1 | Henrico Fall Line Trail Phase 4: Lakeside Community Trail Section III | Off- Road/On-Road Trail | N/A | Lakeside Recreation Area | Hilliard Rd | Henrico | 4749000 | 4749000 | 0 | 0 | 0 | 65 | 1
236 | FPR-2 | Lewistown Rd/Lakeridge Pkwy or Ashland | New P&R Lot of 200 spaces on 1.4 AC | Park & Ride | N/A | NA | NA | Hanover or Ashland | 4967000 | 4967000 | 0 | 0 | 0 | 66 | 1
138 | FHW-138 | US-60 & Judes Ferry Rd | Reconfiguration of the intersections of US Route 60 and Judes Ferry Road into an RCUT | Intersection Improvement | NA | NA | NA | Powhatan | 5353000 | 5353000 | 0 | 0 | 0 | 67 | 1
59 | FHW-59 | I-95 | Widening with added capacity | Road Widening | Both | Exit 62 (VA-288 ) | Exit 64 (Willis Rd) | Chesterfield | 15453000 | 15453000 | 0 | 0 | 0 | 69 | 1
163 | FHW-163 | VA-288 & US-250 | Construction of a dual NB right-turn lanes at the SB VA- 288 ramp intersection and widening the northbound VA- 288 off-ramp to two lanes | Interchange Modification | SB | N/A | N/A | Goochland | 5409000 | 5409000 | 0 | 0 | 0 | 70 | 1
269 | FHW-900 | Elmont Rd | Construction of a new 2-lane road | Road Extension | Both | Medical Dr | VA-54/Vaughan Rd | Ashland | 2181000 | 2181000 | 0 | 0 | 0 | Not Scored | 1 | Ashland Priority Project
270 | FHW-901 | Woolridge Rd | Widening with added capacity | Road Widening | Both | Watermill Pkwy | Genito Rd | Chesterfield | 16883000 | 16883000 | 0 | 0 | 0 | Not Scored | 1 | Chesterfield Priority Project
272 | FHW-903 | VA-76 (Powhite Pkwy Ext) | Powhite Parkway Extension Phase 1. Little Tomahawk Creek to Woolridge Rd (2 to 4 lanes), Charter Colony Pkwy (Grade-Separation), Brandermill Pkwy(Overpass) | Road Extension | Both | Little Tomahawk Creek | Woolridge Rd | Chesterfield | 170000000 | 170000000 | 0 | 0 | 0 | Not Scored | 1 | Chesterfield Priority Project
273 | FHW-904 | VA-76 (Powhite Pkwy Ext) | Powhite Parkway Extension Phase 2. Woolridge Rd to Genito Rd (0-2 Lanes), Otterdale Rd overpass, at-grade Genito Rd intersection. Genito Rd Magnolia Green Pkwy (0 to 2 lanes), at-grade Magnolia Green Pkwy intersection | Road Extension | Both | Woolridge Rd | Magnolia Green Pkwy | Chesterfield | 174000000 | 174000000 | 0 | 0 | 0 | Not Scored | 1 | Chesterfield Priority Project
276 | FTR-901 | NA | Downtown Transfer Center | New Transit Transfer Center | N/A | NA | NA | Richmond | 19869000 | 4082477 | 15786523 | 0 | 0 | Not Scored | 1 | GRTC Priority Project
[9 empty] | 669115000 | 647694562 | 15786523 | 5633915 | 0

## TB2
ConnectRVA 2045 - Cost Constrained List of Regional Projects - Time Band 2 (FY28-FY33) (Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Inflated Cost | Flexible Funds | Transit Funds | Air Quality Funds | Air Quality Funds | Rank | Time -Band | Staff Notes
262 | FTR-5 | Rt 1 North | 15.7 miles from The Pulse BRT downtown to Ashland along US 1 | Bus Rapid Transit | Both | CBD | Ashland | Richmond/ Henrico/ Hanover/ Ashland | 54404000 | 54404000 | 0 | 0 | 0 | 35 | 2 | Moved From Time Band 1
48 | FHW-48 | I-64 | Construction of an auxiliary lane between Welcome Center to Exit 214 (VA-155) | Auxiliary Lane | EB | Welcome Center | Exit 214 (VA-155) | New Kent | 5120000 | 5120000 | 0 | 0 | 0 | 68 | 2 | Moved from Time Band 1 to be with the WB project
151 | FHW-151 | VA-150 & Strathmore Rd | Elimination of On and Off-Ramps | Interchange Modification | SB | NA | NA | Chesterfield | 6400000 | 6400000 | 0 | 0 | 0 | 72 | 2
116 | FHW-116 | US- 301 & VA-54 | Converting "Y" intersection to a roundabout | Intersection Improvement | NA | NA | NA | Hanover | 5760000 | 0 | 0 | 0 | 5760000 | 73 | 2
36 | FHW-36 | I-295 | Widening to a two-lane section from I-95 SB on ramp onto I-295(Exit 43) NB to end of C-D lane (0.5 mi) | Interchange Modification | NB | I-95 SB on ramp | Exit 43 C | Henrico | 10241000 | 10241000 | 0 | 0 | 0 | 74 | 2
241 | FPR-7 | VA-10/VA- 288 at I-95/I-295 | New P&R lot of 250 spaces on 1.7 AC | Park & Ride | NA | NA | NA | Chesterfield | 7168000 | 0 | 0 | 0 | 7168000 | 75 | 2
78 | FHW-78 | Manakin Town Ferry Rd | Construction of a new 2-lane road (0.6 mi) | Road Extension | Both | Page Road | US-60 Aligned with Oakbridge Drive | Powhatan | 6638000 | 6638000 | 0 | 0 | 0 | 76 | 2
235 | FPR-1 | VA Center Commons/I-295/I-95 | New P&R Lot of 380 Spaces on 2.6 AC | Park & Ride | NA | NA | NA | Henrico | 10625000 | 0 | 0 | 0 | 10625000 | 77 | 2
108 | FHW-108 | Shady Grove Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Nuckols Rd | Hanover County line | Henrico | 10241000 | 10241000 | 0 | 0 | 0 | 78 | 2
155 | FHW-155 | VA-161 & Broad Rock Blvd | Construction of a new roundabout | Intersection Improvement | NA | NA | NA | Richmond | 10241000 | 0 | 0 | 0 | 10241000 | 80 | 2
234 | FAT-34 | Wilton on the James Trail | Shared Use Trail | Shared Use Path | NA | VA-5 | James River | Henrico | 6400000 | 0 | 0 | 6400000 | 0 | 81 | 2
263 | FTR-6 | Broad St | 11.5 miles from Willow Lawn to Short Pump | Enhanced route of existing Short Pump route to 15-minute service, transfer at Willow Lawn BRT to Short Pump Town Center | Both | Willow Lawn | Short Pump | Richmond/ Henrico | 30722000 | 0 | 13031461 | 0 | 17690539 | 82 | 2
73 | FHW-73 | Judes Ferry Rd | Widening with added capacity (0.5 mi) | Road Widening | Both | US-60 | Old Church Road | Powhatan | 9503000 | 9503000 | 0 | 0 | 0 | 84 | 2
141 | FHW-141 | US-60 & VA-13 | Construct of a RCUT at the intersection of US-60 and VA-13 (including additional turn lanes | Intersection Improvement | NA | NA | NA | Powhatan | 9214000 | 9214000 | 0 | 0 | 0 | 86 | 2
206 | FAT-6 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 3C - MM 14.9 to MM 16.8 | Off- Road/On-Road Trail | NA | Gettings Ln | Wayside Park/Falling Cr | Chesterfield | 8892000 | 772791 | 0 | 1018452 | 7100757 | 87 | 2
81 | FHW-81 | Meadowbridge Rd | Widening with added capacity (1.35 mi) | Road Widening | Both | Henrico Co. Line | Atlee Rd | Hanover | 17281000 | 17281000 | 0 | 0 | 0 | 88 | 2
102 | FHW-102 | Red Lane Rd | Construction of a new two-lane road to connect Red Lane Road with Lees Landing Road | Road Realignment | Both | Intersection of Three Bridge Road & Lees Landing Road | Red Lane Road 0.6 miles south of its intersection with Three Bridge Road | Powhatan | 8664000 | 8664000 | 0 | 0 | 0 | 89 | 2
56 | FHW-56 | I-64 & US-33 | Addition of a southbound through lane on Staples Mill Road between I-64 west on-ramp and I-64 east on-ramp. New two-phase signal at a widened, 2 lanes to 3 lanes, I-64 off ramp to limit SB weaving. Intersection improvements include added capacity at the US-33 and Bethlehem Rd intersection via additional turn bays and an RCUT/directional median at Millstone Rd | Interchange Modification | NA | NA | NA | Henrico | 20481000 | 20481000 | 0 | 0 | 0 | 90 | 2
87 | FHW-87 | New Road | Construction of a new 2-lane road | New Road | Both | Hockett Rd | Future Wilkes Ridge Parkway Extension | Goochland | 19758000 | 19758000 | 0 | 0 | 0 | 91 | 2
143 | FHW-143 | VA-10 & Walmsley Blvd | Construction of a new roundabout | Intersection Improvement | NA | NA | NA | Richmond | 10241000 | 10241000 | 0 | 0 | 0 | 92 | 2
120 | FHW-120 | US-1 & VA-30 | Reconfiguration from a stop controlled “T” intersection to a “Continuous Green-T” thereby adding a signal and dedicated left and right turn lanes on US-1 | Intersection Improvement | NA | NA | NA | Hanover | 8705000 | 8705000 | 0 | 0 | 0 | 93 | 2
227 | FAT-27 | Cox Rd | Cox Rd Bike Facility | Segregated Bike Lane | NA | US-250 | North end of Cox Rd | Henrico | 11521000 | 11521000 | 0 | 0 | 0 | 94 | 2
69 | FHW-69 | I-95 & VA-54 | Conversion of the interchange to a Diverging Diamond (DDI) (Exit 92) | Interchange Modification | NA | NA | NA | Ashland | 12801000 | 12801000 | 0 | 0 | 0 | 95 | 2
101 | FHW-101 | Pump Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Walbrook Rd | Waltham Dr | Henrico | 9601000 | 9601000 | 0 | 0 | 0 | 97 | 2
258 | FTR-1 | Midlothian | 14.3 miles, from CBD to Stonebridge replace less frequent service with more frequency; new service from Stonebridge to Chesterfield Town Center | Enhanced 15 min transit | Both | CBD | Chesterfield Town Center | Richmond-Chesterfield | 51843000 | 51843000 | 0 | 0 | 0 | 98 | 2
99 | FHW-99 | Pouncey Tract Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Grey Oaks Park Dr | N. Gayton Rd | Henrico | 16641000 | 16641000 | 0 | 0 | 0 | 99 | 2
44 | FHW-44 | I-64 | Construction of an auxiliary lane between Exit 183 (US-250) and Exit 185 (US-33) | Auxiliary Lane | WB | Exit 183 | Exit 185 | Henrico | 35842000 | 35842000 | 0 | 0 | 0 | 100 | 2
21 | FHW-21 | Creighton Rd | Widening with added capacity (1.1mi) | Road Widening | Both | I-295 | Cold Harbor Rd | Hanover | 15361000 | 15361000 | 0 | 0 | 0 | 101 | 2
43 | FHW-43 | I-64 | Construction of an auxiliary lane between Exit 183 (US-250) and Exit 185 (US-33) | Auxiliary Lane | EB | Exit 183 | Exit 185 | Henrico | 34562000 | 34562000 | 0 | 0 | 0 | 102 | 2
207 | FAT-7 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Elliham Avenue to Dwight Avenue | Off- Road/On-Road Trail | NA | Elliham Ave | Dwight Ave | Chesterfield | 10430000 | 10430000 | 0 | 0 | 0 | 103 | 2
100 | FHW-100 | Pouncey Tract Rd | Widening with added capacity (to include center turnlane, two through lanes each direction) and bike/ped facilities | Road Widening | Both | Nuckols Rd | Grey Oaks Park Dr | Henrico | 12801000 | 12801000 | 0 | 0 | 0 | 104 | 2
77 | FHW-77 | Lewistown Rd & Ashcake Rd | Reconfiguration from a stop controlled “T” intersection to a roundabout | Intersection Improvement | NA | NA | NA | Hanover | 12417000 | 12417000 | 0 | 0 | 0 | 105 | 2
76 | FHW-76 | Lauderdale Dr | Widening with added capacity and bike/ped facilities | Road Widening | Both | Westbriar Dr | Eadenbury Dr | Henrico | 10241000 | 10241000 | 0 | 0 | 0 | 106 | 2
114 | FHW-114 | Three Chopt Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Skipwith Rd | Horsepen Rd | Henrico | 19201000 | 19201000 | 0 | 0 | 0 | 108 | 2
41 | FHW-41 | I-64 | Construction of an auxiliary lane between Exit 180 (Gaskins Rd) and Exit 181 (Parham Rd) | Auxiliary Lane | EB | Exit 180 | Exit 181 | Henrico | 27906000 | 27906000 | 0 | 0 | 0 | 109 | 2
159 | FHW-159 | VA-288 | Construction of a new SB Auxiliary Lane (1.4 mi) | Auxiliary Lane | SB | US -250 | Tuckahoe Creek Pkwy | Goochland | 22350000 | 22350000 | 0 | 0 | 0 | 110 | 2
123 | FHW-123 | US-250 & Parham Rd | Operational improvements and pedestrian accommodations | Intersection Improvement | NA | NA | NA | Henrico | 14081000 | 14081000 | 0 | 0 | 0 | 113 | 2
74 | FHW-74 | Judes Ferry Rd | Construction of a new 2-lane road (1.2mi) | Road Extension | Both | Judes Ferry Road 0.4 miles N of Hancock Road | 0.25 mi S of Federal Hill Farms Rd | Powhatan | 14852000 | 14852000 | 0 | 0 | 0 | 114 | 2
181 | FHW-181 | Wilkes Ridge Parkway | Construction of a new 2-lane road | Road Extension | Both | Wilkes Ridge Parkway | Tuckahoe Creek Pkwy | Goochland | 29637000 | 29637000 | 0 | 0 | 0 | 116 | 2
160 | FHW-160 | VA-288 | Construction of a Hard Shoulder Running Auxiliary Lane | Auxiliary Lane | NB | VA-711 (Huguenot Tr) | VA-6 | Goochland/Powhatan | 26786000 | 26786000 | 0 | 0 | 0 | 118 | 2
98 | FHW-98 | Pouncey Tract Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | US-250 | N. Gayton Rd | Henrico | 25602000 | 25602000 | 0 | 0 | 0 | 119 | 2
14 | FHW-14 | Charles City Rd | Widening with added capacity | Road Widening | Both | Laburnum Ave | Monahan Rd | Henrico | 19201000 | 19201000 | 0 | 0 | 0 | 120 | 2
3 | FHW-3 | Ashland Rd | Widening with added capacity | Road Widening | Both | I-64 Ramp NB | I-64 Ramp SB | Goochland | 21633000 | 21633000 | 0 | 0 | 0 | 121 | 2
49 | FHW-49 | I-64 | Construction of an auxiliary lane between Welcome Center to Exit 214 (VA-155) | Auxiliary Lane | WB | Welcome Center | Exit 214 (VA-155) | New Kent | 11521000 | 11521000 | 0 | 0 | 0 | 122 | 2
88 | FHW-88 | Nuckols Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Shady Grove Rd | Springfield Rd | Henrico | 38403000 | 38403000 | 0 | 0 | 0 | 123 | 2
89 | FHW-89 | Oilville Rd | Widening with added capacity | Road Widening | Both | Broad Street Road | I-64 | Goochland | 25556000 | 25556000 | 0 | 0 | 0 | 125 | 2
202 | FAT-2 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Park Ext to Chester Rd. | Off- Road/On-Road Trail | NA | VA-10/W. Hundred Rd | Chester Rd | Chesterfield | 16110000 | 16110000 | 0 | 0 | 0 | 127 | 2
23 | FHW-23 | Creighton Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Sandy Ln | City Limits | Henrico | 17921000 | 17921000 | 0 | 0 | 0 | 128 | 2
233 | FAT-33 | Mountain Rd | Shared Use Trail | Shared Use Path | NA | Woodman Rd | Staples Mill Rd | Henrico | 15361000 | 15361000 | 0 | 0 | 0 | 129 | 2
136 | FHW-136 | US-60 & Belt Blvd | Removal of the existing traffic signals in the vicinity of the interchange at the ramps. Construction of two new roundabouts, one in north and other in south of the bridge. | Interchange Modification | NA | NA | NA | Richmond | 25602000 | 25602000 | 0 | 0 | 0 | 132 | 2
9 | FHW-9 | Carter Gallier Blvd | Construction of a new two lane road from Carter Gallier Boulevard to Luck Stone Road completing a road parallel to US Route 60 | Road Extension | NA | NA | NA | Powhatan | 19653000 | 19653000 | 0 | 0 | 0 | 133 | 2
19 | FHW-19 | Commerce Rd & Walmsley Blvd | Construction of a roundabout at Commerce Rd and Walmsley Boulevard Intersection | Intersection Improvement | NA | NA | NA | Richmond | 16385000 | 16385000 | 0 | 0 | 0 | 134 | 2
93 | FHW-93 | Parham Rd & Patterson Ave | Construction of additional turn lanes and pedestrian accommodations | Intersection Improvement | NA | NA | NA | Henrico | 17921000 | 17921000 | 0 | 0 | 0 | 135 | 2
144 | FHW-144 | VA-106 | Widening of the Bridge Overpass at I-64 | Road Widening | Both | I-64 EB On Ramp | I-64 WB Off Ramp | New Kent | 21004000 | 21004000 | 0 | 0 | 0 | 136 | 2
79 | FHW-79 | Masonic Ln/Brittles Ln | Widening with added capacity and bike/ped facilities | Road Widening | Both | Nine Mile Rd | Williamsburg Rd | Henrico | 33282000 | 33282000 | 0 | 0 | 0 | 137 | 2
184 | FHW-184 | Woodside Ln | Construction of a new 2-lane road (1.1 mi) | Road Extension | Both | Jamestown Rd | Hickory Hill Rd | Hanover | 16001000 | 16001000 | 0 | 0 | 0 | 138 | 2
165 | FHW-165 | VA-288 & US-250 | Construction of a New Directional On-Ramp (1-lane) | Interchange Modification | SB | WB US-250 | SB VA-288 | Goochland | 25410000 | 25410000 | 0 | 0 | 0 | 139 | 2
20 | FHW-20 | Courtney Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Staples Mill Rd | Mountain Rd | Henrico | 16001000 | 16001000 | 0 | 0 | 0 | 140 | 2
125 | FHW-125 | US-33 | Widening with added capacity (1.3 mi) | Road Widening | Both | Overhill Lake Ln | Winns Church Rd | Hanover | 20481000 | 20481000 | 0 | 0 | 0 | 141 | 2
24 | FHW-24 | Darbytown Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | S Laburnum Ave | Doran Rd | Henrico | 23042000 | 23042000 | 0 | 0 | 0 | 142 | 2
34 | FHW-34 | I-295 | Construction of a single northbound auxiliary lane between the onramp from Nuckols Road SB (Exit 51) on-ramp and I-295 NB and I-64 Branch | Auxiliary Lane | NB | Nuckols Rd (Exit 51) | Western Terminus | Henrico | 25602000 | 25602000 | 0 | 0 | 0 | 143 | 2
140 | FHW-140 | US-60 & US-522 | Construction of a roundabout at US- 522 and a quadrant roadway from the roundabout to US-60 at the northeast corner of the intersection. Construction of a CGT at the intersection of the quadrant road and US- 60. | Intersection Improvement | NA | NA | NA | Powhatan | 21889000 | 21889000 | 0 | 0 | 0 | 144 | 2
161 | FHW-161 | VA-288 | Construction of a Hard Shoulder Running Auxiliary Lane | Auxiliary Lane | SB | West Creek Pkwy | VA-711 (Huguenot Tr) | Goochland/Powhatan | 45100000 | 45100000 | 0 | 0 | 0 | 180 | 2 | Moved from Time Band 3 to be with the NB project
271 | FHW-902 | I-64 & Oilville Rd | Construction of a one-lane roundabout at the westbound I-64 ramp at the Oilville Rd. interchange | Interchange Modification | NA | NA | NA | Goochland | 7719000 | 7719000 | 0 | 0 | 0 | Not Scored | 2 | Goochland Priority Project
275 | FTR-900 | NA | Southside Transfer Center | Transit Transfer Center | NA | NA | NA | Richmond | 3840000 | 3840000 | 0 | 0 | 0 | Not Scored | 2 | GRTC Priority Project
[9 empty] | 1195813000 | 1116777791 | 13031461 | 7418452 | 58585296

## TB3
ConnectRVA 2045 - Cost Constrained List of Regional Projects - Time Band 3 (FY34-FY39)(Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Inflated Cost | Flexible Funds | Transit Funds | Active Funds | Air Quality Funds | Rank | Time -Band | Staff Notes
85 | FHW-85 | New Ashcake Rd | Construction of a new 2-lane road (1.75 mi) | Road Extension | Both | New Ashcake Rd | Air Park Rd | Hanover | 29690000 | 29690000 | 0 | 0 | 0 | 145 | 3
22 | FHW-22 | Creighton Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Cedar Fork Rd | Hanover County Line | Henrico | 38597000 | 38597000 | 0 | 0 | 0 | 146 | 3
113 | FHW-113 | Three Chopt Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Gaskins Rd | N Parham Rd | Henrico | 51958000 | 51958000 | 0 | 0 | 0 | 147 | 3
65 | FHW-65 | I-95 & I-64 | Improvement of interchange configuration with I-64 to improve the SB I-95 to WB I-64 ramp (Exit 79). Merge 3 lanes to 2 after on-ramp from Laburnum. 2-lane on-ramp from SB I-95.Convert WB I-64 on-ramp from SB I-95 to two lanes. Remove one lane from WB I-64 prior to on-ramp. | Interchange Modification | NA | NA | NA | Richmond | 74225000 | 74225000 | 0 | 0 | 0 | 150 | 3
66 | FHW-66 | I-95 & Parham Rd | Construction of a new Partial Cloverleaf Interchange (Exit 83). Improve interchange configuration at Parham Road to remove weaving movements. | Interchange Modification | NA | NA | NA | Henrico | 29690000 | 29690000 | 0 | 0 | 0 | 151 | 3
61 | FHW-61 | I-95 & Belvidere St | Improvement of interchange configuration at Belvidere St/Chamberlayne Ave (Exit 76). Construct C-D Road from Exit 76 to Exit 75.Construct SPUI (single Point Urban Interchange) at Belvidere Street and remove the northbound off-ramp to Chamberlayne Avenue. | Interchange Modification | NA | NA | NA | Richmond | 96493000 | 96493000 | 0 | 0 | 0 | 152 | 3
94 | FHW-94 | Pemberton Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Quioccasin Rd | US-250 | Henrico | 62349000 | 62349000 | 0 | 0 | 0 | 154 | 3
2 | FHW-2 | Ashland Rd | Widening with added capacity | Road Widening | Both | Broad Street Rd | I-64 | Goochland | 35560000 | 35560000 | 0 | 0 | 0 | 156 | 3
148 | FHW-148 | VA-150 & Hopkins Rd | Construction of a diverging diamond interchange | Interchange Modification | NA | NA | NA | Chesterfield | 36258000 | 36258000 | 0 | 0 | 0 | 157 | 3
104 | FHW-104 | River Road | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Sleepy Hollow Rd | E/O VA-150 | Henrico | 33401000 | 33401000 | 0 | 0 | 0 | 158 | 3
5 | FHW-5 | Ashland Rd | Widening with added capacity (2.65 mi) | Road Widening | Both | US-33 | Blanton Rd | Hanover | 47504000 | 47504000 | 0 | 0 | 0 | 159 | 3
11 | FHW-11 | Cedar Ln | Widening with added capacity (2.1 mi) | Road Widening | Both | US-1 | Elmont Rd | Hanover | 37113000 | 37113000 | 0 | 0 | 0 | 160 | 3
164 | FHW-164 | VA-288 & US-250 | Construction of a New Directional On-Ramp (1-lane) | Interchange Modification | NB | WB US-250 | NB VA-288 | Goochland | 31175000 | 31175000 | 0 | 0 | 0 | 161 | 3
18 | FHW-18 | Church Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | Three Chopt Rd | John Rolfe Pkwy | Henrico | 46020000 | 46020000 | 0 | 0 | 0 | 162 | 3
111 | FHW-111 | Springfield Rd | Construction of a new two-lane road with bike/ped facilities | Road Relocation | Both | Francistown Rd | Olde Millbrooke Way | Henrico | 37113000 | 37113000 | 0 | 0 | 0 | 163 | 3
95 | FHW-95 | Pole Green Rd | Widening with added capacity (1.85 mi) | Road Widening | Both | Rural Point Rd | Walnut Grove Rd | Hanover | 31175000 | 31175000 | 0 | 0 | 0 | 164 | 3
112 | FHW-112 | Three Chopt Rd | Construction of a new 1,500 ft., two-lane divided road segment to reconnect existing segments of Three Chopt Rd under VA- 288 (underpass) | New Underpass | Both | 0.1 mile west of VA-288 | 0.1 mile east of VA- 288 | Goochland | 27952000 | 27952000 | 0 | 0 | 0 | 165 | 3
52 | FHW-52 | I-64 & Ashland Rd (VA-623) | Reconstruction of the existing Diamond Interchange to a single-lane Diverging Diamond Interchange (DDI) | Interchange Modification | NA | NA | NA | Goochland | 35422000 | 35422000 | 0 | 0 | 0 | 167 | 3
13 | FHW-13 | Charles City Rd | Widening with added capacity | Road Widening | Both | Williamsburg Rd | Eastport Blvd | Henrico | 38597000 | 38597000 | 0 | 0 | 0 | 168 | 3
58 | FHW-58 | I-95 | Construction of an SB auxiliary lane between Exit 67 (VA-150) and Exit 69 (Bells Rd) | Auxiliary Lane | SB | Exit 67 (VA-150) | Exit 69 (Bells Rd) | Chesterfield/Richmond | 37855000 | 37855000 | 0 | 0 | 0 | 169 | 3
42 | FHW-42 | I-64 | Construction of an auxiliary lane between Exit 181 (Parham Rd) and Exit 183 (US-250) | Auxiliary Lane | EB | Exit 181 | Exit 183 | Henrico | 76304000 | 76304000 | 0 | 0 | 0 | 170 | 3
153 | FHW-153 | VA-150 & US-360 | Removal of SE, NE loops and signalization of NB ramp terminal | Interchange Modification | NA | NA | NA | Chesterfield | 48989000 | 48989000 | 0 | 0 | 0 | 172 | 3
54 | FHW-54 | I-64 & Parham Rd | Improvement of Interchange Configuration. Widening EB ramp terminal to include dual right turn lanes | Interchange Modification | NA | NA | NA | Henrico | 37113000 | 37113000 | 0 | 0 | 0 | 174 | 3
231 | FAT-31 | Route 155 | Connection between Charles City and New Kent courthouses (spur from Virginia Capital Trail) | Off Road Trail | NA | VA-5(Charles City Schools) | New Kent County Line | Charles City | 24940000 | 16731968 | 0 | 8208032 | 0 | 175 | 3
6 | FHW-6 | Atlee Station Rd | Widening with added capacity (1.5 mi) | Road Widening | Both | Kings Charter Dr | Sliding Hill Rd | Hanover | 47504000 | 47504000 | 0 | 0 | 0 | 176 | 3
96 | FHW-96 | Pole Green Rd | Widening with added capacity (2.15 mi) | Road Widening | Both | Walnut Grove Rd | US-360 | Hanover | 35628000 | 35628000 | 0 | 0 | 0 | 177 | 3
84 | FHW-84 | N Gayton Rd | Widening with added capacity (to include center turnlane, one through lanes each direction) and bike/ped facilities | Road Widening | Both | US-250 | Lauderdale Dr | Henrico | 34144000 | 34144000 | 0 | 0 | 0 | 178 | 3
118 | FHW-118 | US-1 | Widening with added capacity | Road Widening | Both | US-54 | Archie Cannon Dr | Ashland | 34144000 | 34144000 | 0 | 0 | 0 | 179 | 3
154 | FHW-154 | VA-150 & US-60 | Construction of a Partial Cloverleaf Interchange with contraflow left turns | Interchange Modification | NA | NA | NA | Chesterfield | 50612000 | 50612000 | 0 | 0 | 0 | 184 | 3
126 | FHW-126 | US-33 | Widening with added capacity (2.4 mi) | Road Widening | Both | Winns Church Rd | Ashland Rd | Hanover | 43051000 | 43051000 | 0 | 0 | 0 | 187 | 3
157 | FHW-157 | VA-288 | Widening with added capacity | Road Widening | Both | VA-76 (Powhite Pkwy) | US-360 | Chesterfield | 63388000 | 63388000 | 0 | 0 | 0 | 188 | 3
106 | FHW-106 | Rural Point Rd | Widening with added capacity (2.1 mi) | Road Widening | Both | Studley Rd | Pole Green Rd | Hanover | 37113000 | 37113000 | 0 | 0 | 0 | 189 | 3
10 | FHW-10 | Cauthorne Rd | Widening with added capacity (4.0 mi) | Road Widening | Both | Ashland Rd | Henrico Co. Line | Hanover | 41566000 | 41566000 | 0 | 0 | 0 | 191 | 3
1 | FHW-1 | Archie Cannon Dr | Construction of a bridge over CSX RR | New Overpass | Both | NA | NA | Ashland | 38597000 | 38597000 | 0 | 0 | 0 | 192 | 3
265 | FTR-8 | West End South | 15.85 miles enhanced 15-min service | Combination of enhanced existing route to Regency and extension to Gayton Crossing | Both | Cary/Main | Gayton Crossing | Richmond/ Henrico | 198924000 | 121950571 | 12152635 | 0 | 64820794 | 211 | 3 | Moved From Time Band 4 to accommodate Air Quality Funds
[9 empty] | 1670164000 | 1584982539 | 12152635 | 8208032 | 64820794

## TB4
ConnectRVA 2045 - Cost Constrained List of Regional Projects - Time Band 4 (FY40-FY45)(Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Inflated Cost | Flexible Funds | Transit Funds | Active Funds | Air Quality Funds | Rank | Time -Band | Staff Notes
205 | FAT-5 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Segment 3B - MM 13.6 to MM 14.9 | Off- Road/On-Road Trail | NA | US-1/Kingsdale Rd | Gettings Ln | Chesterfield | 6679000 | 0 | 0 | 0 | 6679000 | 54 | 4 | Moved From Time Band 4 to accommodate Air Quality Funds
260 | FTR-3 | RIC Airport | 10.5 miles from CBD to Airport via Williamsburg Rd | Enhanced Route 7A/7B-15 min transit | Both | CBD | RIC Airport | Richmond/ Henrico | 41318000 | 0 | 12315235 | 0 | 29002765 | 107 | 4 | Moved From Time Band 4 to accommodate Transit and Air Quality Funds
222 | FAT-22 | Fall Line / Route 1 | Henrico Fall Line Trail Phase 7: Longdale | Off- Road/On-Road Trail | NA | Parham Rd | Woodman Rd Extended | Henrico | 44772000 | 0 | 0 | 9081650 | 35690350 | 181 | 4 | Moved From Time Band 4 to accommodate Air Quality Funds
103 | FHW-103 | Richmond Henrico Tpk | Widening with added capacity and bike/ped facilities | Road Widening | Both | Hanover County Line | Railroad Crossing | Henrico | 51647000 | 51647000 | 0 | 0 | 0 | 193 | 4
135 | FHW-135 | US-60 | Widen bridge over Belt Blvd and extend deceleration and acceleration lanes over CSX | Road Widening | Both | Division Street | CSX RR | Richmond | 68863000 | 68863000 | 0 | 0 | 0 | 194 | 4
28 | FHW-28 | Greenwood Rd | Widening with added capacity and bike and pedestrian accommodations | Road Widening | Both | Woodman Road | County Line | Henrico | 70584000 | 70584000 | 0 | 0 | 0 | 195 | 4
183 | FHW-183 | Woodman Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Mountain Rd | Hungary Rd | Henrico | 77471000 | 77471000 | 0 | 0 | 0 | 196 | 4
53 | FHW-53 | I-64 & Gaskins Rd | Improvement of Interchange Configuration. Convert Interchange to Partial-Cloverleaf. Removal of eastbound I-64 off-ramp to northbound Gaskins Road loop ramp and the westbound I-64 off-ramp to southbound Gaskins Road loop ramp. Allow left turn movements from the remaining eastbound and westbound I-64 off-ramps by installing left turn lanes and signalized ramp terminals. | Interchange Modification | NA | NA | NA | Henrico | 82291000 | 82291000 | 0 | 0 | 0 | 197 | 4
105 | FHW-105 | Rural Point Rd | Widening with added capacity (2.6 mi) | Road Widening | Both | US-301 | Studley Rd | Hanover | 53369000 | 53369000 | 0 | 0 | 0 | 199 | 4
4 | FHW-4 | Ashland Rd | Widening with added capacity (3.7 mi) | Road Widening | Both | Henrico Co. Line | US-33 | Hanover | 74888000 | 74888000 | 0 | 0 | 0 | 200 | 4
8 | FHW-8 | Carolina Ave | Widening with added capacity and bike/ped facilities | Road Widening | Both | Richmond Henrico Tpk | Laburnum Ave | Henrico | 61288000 | 61288000 | 0 | 0 | 0 | 201 | 4
117 | FHW-117 | US-1 | Widening with added capacity | Road Widening | Both | Ashcake Rd | Sourthern Town Limits | Ashland | 62493000 | 62493000 | 0 | 0 | 0 | 203 | 4
67 | FHW-67 | I-95 & VA-10 | Construction of a new Partial Cloverleaf Interchange (Exit 61) Reconfigure interchange ramps to accommodate the partial cloverleaf configuration  Eliminate southbound I-95 to eastbound Route 10 off-ramp  Eliminate northbound I-95 to westbound Route 10 off-ramp  Realign westbound Route 10 to northbound I-95 on-ramp | Interchange Modification | NA | NA | NA | Chesterfield | 90457000 | 90457000 | 0 | 0 | 0 | 207 | 4
127 | FHW-127 | US-360 | Widening with added capacity | Road Widening | Both | E. of Cosby Rd | Magnolia Green Pkwy | Chesterfield | 72995000 | 72995000 | 0 | 0 | 0 | 208 | 4
75 | FHW-75 | Judes Ferry Rd | Construction of a new 4-lane road (1.8 mi) | Road Extension | Both | US-60 | Dorset Rd | Powhatan | 58516000 | 58516000 | 0 | 0 | 0 | 212 | 4
152 | FHW-152 | VA-150 & US-1 | Reconfiguration of the interchange to partial cloverleaf | Interchange Modification | NA | NA | NA | Chesterfield | 56812000 | 56812000 | 0 | 0 | 0 | 213 | 4
40 | FHW-40 | I-64 | Construction of an EB & WB auxiliary lane between Exit 178 (US-250) and Exit 180 (Gaskins Rd). Reconstruction of Cox Rd Bridge. Widening of EB US-250 (W Broad Street/Short Pump) to EB I-64 ramp to two lane. | Auxiliary Lane | Both | Exit 178 | Exit 180 | Henrico | 129634000 | 129634000 | 0 | 0 | 0 | 214 | 4
131 | FHW-131 | US-360 & Various | Construction of US-360 Superstreet at Winterpock Road, Spring Run Road, Chital Drive, Deer Run Road, and Harbor Pointe Parkway | Intersection Improvement | NA | NA | NA | Chesterfield | 92621000 | 92621000 | 0 | 0 | 0 | 215 | 4
166 | FHW-166 | VA-288 & US-360 | 1) Construction of Route 288 NB Flyover Ramp (1 lane) widening to 2 lanes at partial Diverging Diamond Interchange (DDI), 2) Reconstruction of SB on-ramp, 3) Realignment and widening of SB off-ramp to 2 lanes before DDI, 4) Roundabouts: Bailey Bridge Connector at Commonwealth Centre Connector (2 lane), Commonwealth Centre Connector at Commonwealth Centre Parkway (1 lane) , 5) Cul-de-sac Commonwealth Centre Parkway | Interchange Modification | NA | NA | NA | Chesterfield | 87972000 | 87972000 | 0 | 0 | 0 | 216 | 4
32 | FHW-32 | I- 64 & N. Gayton Rd | Construction of a new Interchange at I-64 in Short Pump | New Interchange | NA | NA | NA | Henrico | 163549000 | 163549000 | 0 | 0 | 0 | 217 | 4
121 | FHW-121 | US-1 & West Hundred Rd | Construction of Innovative Intersection: Median u-turns all approaches | Intersection Improvement | NA | NA | NA | Chesterfield | 77471000 | 77471000 | 0 | 0 | 0 | 218 | 4
46 | FHW-46 | I-64 | Widening with added capacity (5.9 mi) | Road Widening | EB | Exit 205 (Bottoms Bridge) | Exit 211 (VA-106) | New Kent | 126458000 | 126458000 | 0 | 0 | 0 | 220 | 4
47 | FHW-47 | I-64 | Widening with added capacity (5.9 mi) | Road Widening | WB | Exit 205 (Bottoms Bridge) | Exit 211 (VA-106) | New Kent | 129309000 | 129309000 | 0 | 0 | 0 | 221 | 4
72 | FHW-72 | I-95 & Willis Rd | Construction of a new Double Roundabout Interchange (Exit 64) | Interchange Modification | NA | NA | NA | Chesterfield | 116169000 | 116169000 | 0 | 0 | 0 | 222 | 4
180 | FHW-180 | Walmsley Blvd | Construction of a new 2-lane road | Road Extension | Both | US-1 | Commerce Road. | Richmond | 90038000 | 90038000 | 0 | 0 | 0 | 230 | 4 | Richmond Priority Project
[9 empty] | 1987664000 | 1894895000 | 12315235 | 9081650 | 71372115

## SGR
ConnectRVA 2045 - Cost Constrained List of Regional Projects - State of Good Repair (SGR)/Bridge Projects (Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Inflated Cost | SGR Funds | Rank | Time -Band
185 | FBR-1 | US-1 | Bridge - Replacement/Rehabilitation - Jeff Davis Hwy @ Ashton Creek | Bridge | Both | NA | NA | Chesterfield | 3027000 | 3027000 | Not Scored | NA
186 | FBR-2 | I-64 | Bridge - Replacement/Rehabilitation - Wbl I-64 @ Airport Drive (VA-156) | Bridge | WB | NA | NA | Henrico | 44803000 | 44803000 | Not Scored | NA
187 | FBR-3 | I-195 | Bridge - Replacement/Rehabilitation - I-195 @ VA- 197 & CSX | Bridge | Both | NA | NA | Henrico | 17219000 | 17219000 | Not Scored | NA
188 | FBR-4 | VA-73 | Bridge - Replacement/Rehabilitation - Parham Road @ CSX Railway | Bridge | Both | NA | NA | Henrico | 2944000 | 2944000 | Not Scored | NA
189 | FBR-5 | I-64 | Bridge - Replacement/Rehabilitation - Ebl I-64 @ Airport Drive (VA-156) | Bridge | EB | NA | NA | Henrico | 17210000 | 17210000 | Not Scored | NA
190 | FBR-6 | US-60 | Bridge - Replacement/Rehabilitation - Ebl Pocahontas Tr @ Toe Ink Swamp | Bridge | EB | NA | NA | New Kent | 3912000 | 3912000 | Not Scored | NA
191 | FBR-7 | US-250 | Bridge - Replacement/Rehabilitation - Broad Street @ I-95 | Bridge | Both | NA | NA | Richmond | 17503000 | 17503000 | Not Scored | NA
192 | FBR-8 | VA-147 | Bridge - Replacement/Rehabilitation - Cary Street @ I-195 & CSX Railroad | Bridge | Both | NA | NA | Richmond | 15035000 | 15035000 | Not Scored | NA
193 | FBR-9 | US-360 | Bridge - Replacement/Rehabilitation - 14th Street @ James River South Div | Bridge | SB | NA | NA | Richmond | 30722000 | 30722000 | Not Scored | NA
194 | FBR-10 | US-250 | Bridge - Replacement/Rehabilitation - Broad Street @ CSX Abandoned Spur Line | Bridge | Both | NA | NA | Richmond | 5076000 | 5076000 | Not Scored | NA
195 | FBR-11 | US-360 | Bridge - Replacement/Rehabilitation - 14th Street @ James River North Div | Bridge | NB | NA | NA | Richmond | 20481000 | 20481000 | Not Scored | NA
196 | FBR-12 | I-64 | Bridge - Replacement/Rehabilitation - Wbl I-64 @ I- 95 | Bridge | WB | NA | NA | Richmond | 5952000 | 5952000 | Not Scored | NA
197 | FBR-13 | I-195 | Bridge - Replacement/Rehabilitation - Sbl I-195 @ VA- 76, CSX Rr & Ramp S | Bridge | SB | NA | NA | Richmond | 40325000 | 40325000 | Not Scored | NA
198 | FBR-14 | I-64 | Bridge - Replacement/Rehabilitation - Ramp To 5th & I-95S @ I-95 | Bridge | SB | NA | NA | Richmond | 13875000 | 13875000 | Not Scored | NA
199 | FBR-15 | VA-161 | Bridge - Replacement/Rehabilitation - North Boulevard @ CSX Railway | Bridge | Both | NA | NA | Richmond | 17921000 | 17921000 | Not Scored | NA
200 | FBR-16 | VA-161 | Bridge Replacement with Shared Used Path - Westover Hills Blvd (RMTA) @ James River | Bridge | Both | NA | NA | Richmond | 38403000 | 38403000 | Not Scored | NA
[9 empty] | 294408000 | 294408000

## Local-Private
ConnectRVA 2045 - Local/ Private Funded Regional Projects (Draft 6-18-2021)
Project ID | SN | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Cost | Private/Local Funds
P-1 | 278 | Magellan Pkwy Extension | Magellan Pkwy Extension Phase 1 (Retreat @ One) | Road Extension | Both | Park Central Dr | Green City | Henrico | 10000000 | 10000000
P-2 | 279 | Magellan Pkwy Extension | Magellan Pkwy Extension Phase 3 (East of I-95) | Road Extension | Both | I-95 | US-1 | Henrico | 11000000 | 11000000
P-3 | 280 | Oak Hill | Construction of a new 2-lane road | New Road | Both | VA-6 | West Creek Pkwy | Goochland | NA | NA
P-4*( FHW-92) | 92 | Otterdale Rd | Widening with added capacity | Road Widening | Both | US-360 | Woolridge Rd | Chesterfield | 11500000 | 11500000
[9 empty] | 32500000 | 32500000
Note * Also in Universe of Projects - (Project ID FHW-92)

## Vision
ConnectRVA 2045 - Vision List of Regional Projects (Draft 6-18-2021)
SN (UoP) | Project ID | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Rank | Project Total Cost (2020 Dollars) | Project Total Cost (Inflated to 2030 Dollars) | Time -Band | Staff Notes
80 | FHW-80 | Maury St | Widening with added capacity | Road Widening | Both | I-95 roundabout | Commerce Rd | Richmond | 28 | 5000000 | 6400000 | Vision | Not a Priority for the Project Champion
16 | FHW-16 | Chester Rd | Widening with added capacity | Road Widening | Both | VA-288 | Kingsdale Rd | Chesterfield | 79 | 10000000 | 12801000 | Vision | Project Swapped to the Vision List by Project Champion
15 | FHW-15 | Chester Rd | Widening with added capacity | Road Widening | Both | Wood Dale Rd | W Hundred Rd | Chesterfield | 85 | 10000000 | 12801000 | Vision | Project Swapped to the Vision List by Project Champion
259 | FTR-2 | Midlothian | 16.8 miles from the Pulse downtown station(s) to Westchester Commons, via Hull Street | Bus Rapid Transit | Both | CBD | Westchester Commons | Richmond/ Chesterfield | 126 | 97500000 | 124808000 | Vision | BRT route to be implemented once the corridor has enhanced transit. Enhanced Transit project in the Constrained List
50 | FHW-50 | I-64 | Widening with added capacity (2.9 mi) | Road Widening | EB | Exit 211 (VA-106) | Exit 214 (VA-155) | New Kent | 148 | 25000000 | 32002000 | Vision | Cumulative Project. The First Section in the Constrained List
264 | FTR-7 | Broad St | 9.8 miles extension of The Pulse BRT at Willow Lawn to Short Pump Mall | Bus Rapid Transit | Both | Willow Lawn | Short Pump | Richmond/ Henrico | 149 | 125000000 | 160011000 | Vision | BRT route to be implemented once the corridor has enhanced transit. Enhanced Transit project in the Constrained List
51 | FHW-51 | I-64 | Widening with added capacity (2.9 mi) | Road Widening | WB | Exit 211 (VA-106) | Exit 214 (VA-155) | New Kent | 153 | 25000000 | 32002000 | Vision | Cumulative Project. The First Section in the Constrained List
17 | FHW-17 | Chester Rd | Widening with added capacity | Road Widening | Both | Kingsdale Rd | US-1 | Chesterfield | 155 | 20000000 | 25602000 | Vision | Project Swapped to the Vision List by Project Champion
82 | FHW-82 | Midview Rd | Widening with added capacity and bike/ped facilities | Road Widening | Both | New Market Rd | Darbytown Rd | Henrico | 171 | 25000000 | 32002000 | Vision | Public Opposition
266 | FTR-9 | West End South | 18.1 miles from Cary and Main/Patterson/Regency Mall to Short Pump Mall | Bus Rapid Transit | Both | Cary/Main | Short Pump | Richmond/ Henrico | 173 | 160000000 | 204814000 | Vision | BRT route to be implemented once the corridor has enhanced transit. Enhanced Transit project in the Constrained List
133 | FHW-133 | US-60 | Widening with added capacity | Road Widening | Both | Page Rd | Watkins Center Pkwy | Chesterfield | 183 | 33000000 | 42243000 | Vision | Project Swapped to the Vision List by Project Champion
167 | FHW-167 | VA-288 & US-360 | Construction of a EB US-360 to NB VA-288 Directional on-ramp (2 lanes) | Interchange Modification | NA | NA | NA | Chesterfield | 185 | 29500000 | 37762000 | Vision | Project Swapped to the Vision List by Project Champion
91 | FHW-91 | Osborne Turnpike (VA-5) | Widening with added capacity and pedestrian accommodations | Road Widening | Both | New Market Rd | Richmond City Limits | Henrico | 190 | 20000000 | 25602000 | Vision | Public Opposition
179 | FHW-179 | VA-895 & Wilton Rd | Construction of a New Interchange | New Interchange | NA | NA | NA | Henrico | 198 | 60000000 | 76805000 | Vision | Not a Priority for the Project Champion
162 | FHW-162 | VA-288 & Courthouse Rd. | Improvement of WB 288 to NB Courthouse off ramp, extension of decel lane and addition of dual right turns | Interchange Modification | NA | NA | NA | Chesterfield | 202 | 25000000 | 32002000 | Vision | Project Swapped to the Vision List by Project Champion
145 | FHW-145 | VA-150 & Belmont Rd | Extension of acceleration and deceleration lanes for ramps | Interchange Modification | NA | NA | NA | Chesterfield | 204 | 25000000 | 32002000 | Vision | Project Swapped to the Vision List by Project Champion
149 | FHW-149 | VA-150 & N. Huguenot Rd | Construction of a Full Cloverleaf Interchange without traffic signals | Interchange Modification | NA | NA | NA | Richmond | 205 | 30000000 | 38403000 | Vision | Project Swapped to the Vision List by Project Champion
158 | FHW-158 | VA-288 | Widening with added capacity | Road Widening | EB | Courthouse Rd | VA-10 | Chesterfield | 206 | 45000000 | 57604000 | Vision | Project Swapped to the Vision List by Project Champion
226 | FAT-26 | James River Heritage Trail | James River Heritage Trail : Henrico | Off Road Trail | NA | Richmond City Line | Goochland County Line | Henrico | 209 | 30000000 | 38403000 | Vision | Not a Priority for the Project Champion
142 | FHW-142 | VA-10 | Widening with added capacity | Road Widening | Both | Jessup Rd | VA-288 | Chesterfield | 210 | 55000000 | 70405000 | Vision | Project Swapped to the Vision List by Project Champion
268 | FTR-11 | Broad St East | Old Osborne Turnpike BRT Extension | Bus Rapid Transit | Both | Rocketts Landing | Wilton on the James | Henrico | 223 | 30000000 | 38403000 | Vision | Cut-off for the Vision List
168 | FHW-168 | VA-288 & US-360 | Construction of SB VA-288 CD Road (2 lanes) | Interchange Modification | NA | NA | NA | Chesterfield | 224 | 43700000 | 55940000 | Vision
31 | FHW-31 | Huguenot Rd & Robious Rd | Construction of Innovative intersection: Quadrants NW and SE | Intersection Improvement | NA | NA | NA | Chesterfield | 225 | 45000000 | 57604000 | Vision
128 | FHW-128 | US-360 | Widening with added capacity (2.35 mi) | Road Widening | Both | Sujen Ct | Walnut Grove Rd | Hanover | 226 | 50000000 | 64004000 | Vision
38 | FHW-38 | I-295 & Varina Rd | Construction of a new Interchange | New Interchange | NA | NA | NA | Henrico | 227 | 60000000 | 76805000 | Vision
25 | FHW-25 | Darbytown Rd | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Richmond City Line | Laburnum Ave | Henrico | 228 | 65000000 | 83205000 | Vision
37 | FHW-37 | I-295 & Portugee Rd | Construction of a new Interchange | New Interchange | NA | NA | NA | Henrico | 229 | 60000000 | 76805000 | Vision
12 | FHW-12 | Cedar Ln | Widening with added capacity (4.0mi) | Road Widening | Both | Elmont Rd | Ashland Rd | Hanover | 231 | 48000000 | 61444000 | Vision
134 | FHW-134 | US-60 | Widening with added capacity | Road Widening | Both | Elko Rd | New Kent Co Line | Henrico | 233 | 65000000 | 83205000 | Vision
71 | FHW-71 | I-95 & VA-895 | Construction of the missing SB to EB movement at I-95 & VA-895 | Interchange Modification | NA | NA | NA | Richmond | 234 | 23309000 | 29837000 | Vision
170 | FHW-170 | VA-6 | Widening with added capacity | Road Widening | Both | Maidens Rd | Hermitage Rd | Goochland | 235 | 86390500 | 110587000 | Vision | Public Opposition
130 | FHW-130 | US-360 & Commonwealth Center Pkwy | Construction of a Grade Separated Diverging Diamond Interchange | New Interchange | NA | NA | NA | Chesterfield | 236 | 136500000 | 174732000 | Vision
86 | FHW-86 | New Market Rd (VA-5) | Widening with added capacity and pedestrian accommodations | Road Widening | Both | Osborne Turnpike | I-295 | Henrico | 237 | 127000000 | 162571000 | Vision
60 | FHW-60 | I-95 & Bellemeade Rd | Construction of a new I-95 Interchange | New Interchange | NA | NA | NA | Richmond | 238 | 125000000 | 160011000 | Vision
55 | FHW-55 | I-64 & US-250 | Improvement of Interchange Configuration. Convert existing Interchange to Partial-Cloverleaf Eastbound US 250 to Eastbound I-64 -Restriping the middle eastbound US 250 through lane toa shared through/right to allow two lanes to exit for eastbound I-64. Widening the eastbound US 250 ramp to eastbound I-64 to two lanes. Extending the two-lane on-ramp to merge onto I-64 and provide an additional travel lane between the US 250 and Gaskins Road interchanges. Remove EB US 250 to WB I-64 Loop Ramp. Install Dual Left Turn Lane and a Traffic Signal. | Interchange Modification | NA | NA | NA | Henrico | 239 | 160000000 | 204814000 | Vision
62 | FHW-62 | I-95 & Broad Street/ I-64 | Improvement of interchange configuration at Broad Street and I-64 (Exit 74 to Exit 75).Remove ramp from 7th St to EB I-64. Convert NB off-ramp to EB I-64 to two lanes (1 choose) and carry two lanes to existing 2-lane bridge. Consolidate access points for Exit 74 and Exit 75 and Replace with NB CD System. | Interchange Modification | N/A | N/A | N/A | Richmond | 241 | NA | NA | Vision | No Cost Estimates
63 | FHW-63 | I-95 & Hermitage Rd/ US -1 | Removal of northbound off-ramps and southbound on-ramps at Hermitage Rd and at Brook Rd, and relocation to Dumbarton Interchange (Exits 80-81). Construct two-lane on-ramp from EB I-64 and remove off-ramp at Exit 80. Construct off-ramp to Dumbarton Road. Add additional lane to on-ramp from EB I-64. Construct braided ramps to remove weave on interstate. | Interchange Modification | N/A | N/A | N/A | Henrico/Richmond | 241 | NA | NA | Vision | No Cost Estimates
64 | FHW-64 | I-95 & I-295 | Improve interchange configuration with I-295 by adding a NB C-D Road (Exit 84) | Interchange Modification | N/A | N/A | N/A | Henrico | 241 | NA | NA | Vision | No Cost Estimates
249 | FRA-1 | CSX | Improvements to CSX Bellwood Sub (S-Line) to support increased passenger rail service. Construction of additional trackage along CSX Bellwood Sub (S-Line) and bridge over James River as part of Transforming Rail in Virginia initiative. | Rail Enhancement - Capacity | NA | NA | NA | Multi-Jurisdictional | Not Scored | 500000000 | 640042000 | Vision | Rail Project
250 | FRA-2 | CSX | CSX S-Line Crossing Improvements. Grade separate or gate key crossings as they relate to increased usage of the CSX Bellwood Sub (S-line) for both freight & future passenger rail per Transforming Rail in Virginia initiative | Rail Enhancement- Grade Separation | NA | NA | NA | Multi-Jurisdictional | Not Scored | 66250000 | 84806000 | Vision | Rail Project
251 | FRA-3 | CSX | Improvements to CSX Bellwood Sub (S-Line).Construction of sidings and leads as needed to provide rail access to Alleghany Warehouse and Altria / DuPont development areas along Commerce Road. | Rail Industrial Access | NA | NA | NA | Richmond | Not Scored | 2690000 | 3443000 | Vision | Rail Project
252 | FRA-4 | CSX | Improvements to CSX Peninsula Sub line. Construction of sidings and leads as needed to provide rail access to select parcels within RIC/White Oak area | Rail Industrial Access | NA | NA | NA | Henrico | Not Scored | 6000000 | 7681000 | Vision | Rail Project
253 | FRA-5 | NC | Improvements to NS Burkeville to West Point line. Construction of sidings and leads as needed to provide rail access to select parcels within RIC/White Oak area | Rail Industrial Access | NA | NA | NA | Henrico | Not Scored | 3000000 | 3840000 | Vision | Rail Project
254 | FRA-6 | CSX | Improvements in Hanover Siding. Construction of 2.9 miles of third track between the South Anna River and W. Vaughan Road. Construction of a single-track bridge at Elletts Crossing Road. Modify the at-grade crossing at Vaughan Road and reconstruct the roadway bridge at Washington Highway to accommodate the proposed third track between South Anna River and W. Vaughan Road | Rail Enhancement -Capacity | NA | NA | NA | Hanover/Ashland | Not Scored | 60000000 | 76805000 | Vision | Rail Project
255 | FRA-7 | CSX | Replacement of existing Staples Mill AMTRAK Station-Phase I-Site Work and Building replacement (30% prelim DD 2026 estimate) | Rail Enhancement -Station Improvement | NA | NA | NA | Henrico | Not Scored | 259000000 | 331542000 | Vision | Rail Project
256 | FRA-8 | CSX | Replacement of existing Staples Mill AMTRAK Station-Phase II- Track relocation, platform (30% prelim DD-2030 estimate) | Rail Enhancement -Station Improvement | NA | NA | NA | Henrico | Not Scored | 397000000 | 508194000 | Vision | Rail Project
257 | FRA-9 | CSX | Replacement of existing Staples Mill AMTRAK Station-Phase III-Related land for full function (30% prelim DD-later years as per full build-out) | Rail Enhancement -Station Improvement | NA | NA | NA | Henrico | Not Scored | 79000000 | 101127000 | Vision | Rail Project
274 | FHW-905 | VA-76 (Powhite Pkwy Ext) | Powhite Parkway Extension Phase 3, Magnolia Green Pkwy to US-360 (0 to 2 Lnaes), at-grade intersection at US-360 | Road Extension | Both | Magnolia Green Pkwy | US-360 | Chesterfield | Not Scored | 54000000 | 69125000 | Vision | New Project listed in the Vision List
277 | FHW-906 | Magellan Pkwy Extension | Magellan Pkwy Extension Phase 2 (Bridge and Approaches) | Road Extension | Both | Green City | I-95 | Henrico | Not Scored | 24000000 | 30722000 | Vision | New Project listed in the Vision List
[10 empty] | 3430839500 | 4391768000

## Removed-Regrouped
ConnectRVA 2045 - Removed/Regrouped Projects
Project ID | SN | Route/Corridor/ Intersection/ Interchange | Project Description | Project Type | Direction | From | To | Jurisdiction | Connect RVA 2045 Project Rank | Status | Staff Notes
FAT-29 | 229 | Ashcake Rd | Spur to Fall Line | On Road Trail | NA | Giddy Up Ln | US- 1 | Ashland | 49 | Project in the Committed List | Project in the FY22-27 SYIP
FTR-4 | 261 | Rt 1 North | 10.77 miles from CBD to Parham Road | Enhanced Route along existing from CBD to Wilmer/Chamberlayne and then extended to Parham Road | Both | CBD | Parham Road | Richmond/ Henrico | 56 | Project Removed | BRT Project in the same corridor included in the Constrained list
FAT-23 | 223 | Fall Line / Route 1 | Henrico Fall Line Trail Phase 8: Chickahominy River Crossing | Off- Road/On-Road Trail | NA | Woodman Rd Extended | Cedar Ln | Henrico/ Hanover | 71 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-92 | 92 | Otterdale Rd | Widening with added capacity | Road Widening | Both | US-360 | Woolridge Rd | Chesterfield | 83 | Project in Local/Private List | Project Funded by Private Funds
FHW-109 | 109 | Sliding Hill Rd & Ashcake Rd | Reconfiguration of a 2-way stop controlled intersection to a roundabout | Intersection Improvement | NA | NA | NA | Hanover | 96 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-27 | 27 | Fairground Rd | Construction of a new 2-lane road | Road Extension | Both | Sandy Hook Rd | River Road West | Goochland | 111 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-57 | 57 | I-95 | Construction of an auxiliary lane between Exit 61 (VA-10) and Exit 62 (VA-288) | Auxiliary Lane | Both | Exit 61 (VA-10) | Exit 62 (VA-288) | Chesterfield | 112 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-115 | 115 | Tuckahoe Creek Pkwy | Construction of a new 2-lane road | Road Extension | Both | Tuckahoe Creek Parkway | Ridgefield Pkwy (Henrico County) | Goochland | 115 | Project Removed | Project Opposed by Project Champion
FHW-173 | 173 | VA-76 & VA-150 | Construction of a choice lane at SB VA- 150 off loop ramp diverge | Interchange Modification | SB | NA | NA | Chesterfield | 117 | Project in the Committed List | Project in the FY22-27 SYIP
FAT-11 | 211 | Fall Line / Route 1 | Richmond Fall Line Trail: Walmsley to Bellemeade | Off- Road/On-Road Trail | NA | Walmsley Blvd | Bellemeade Rd | Richmond | 124 | Project in the Committed List | Project in the FY22-27 SYIP
FAT-9 | 209 | Fall Line / Route 1 | Chesterfield Fall Line Trail: Falling Creek Ave. to Food Lion | Off- Road/On-Road Trail | NA | Falling Creek Ave | Food Lion | Chesterfield | 130 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-172 | 172 | VA-76 & VA-150 | Construction of a choice lane at NB VA- 150 off loop ramp diverge. Widening of NB VA-76 express lane to 3 lanes to VA- 150 interchange | Interchange Modification | NB | NA | NA | Chesterfield | 131 | Project in the Committed List | Project in the FY22-27 SYIP
FHW-175 | 175 | VA-76 (Powhite Pkwy) | Construction of a new At-Grade 4-lane road | Road Extension | Both | Little Tomahawk Creek | Otterdale Road | Chesterfield | 166 | Project Regrouped | Regrouped Project Included in the constrained/Vision List
FHW-178 | 178 | VA-76 (Powhite Pkwy) | Construction of a new At-Grade 4-lane road | Road Extension | Both | Duval Road | US-360 | Chesterfield | 182 | Project Regrouped | Regrouped Project Included in the constrained/Vision List
FHW-171 | 171 | VA-76 & Charter Colony Pkwy | Construction of a Grade- Separated Diverging Diamond Interchange | New Interchange | NA | NA | NA | Chesterfield | 186 | Project Regrouped | Regrouped Project Included in the constrained/Vision List
FHW-176 | 176 | VA-76 (Powhite Pkwy) | Construction of a new At-Grade 4-lane road | Road Extension | Both | Otterdale Road | Genito Road | Chesterfield | 219 | Project Regrouped | Regrouped Project Included in the constrained/Vision List
FHW-177 | 177 | VA-76 (Powhite Pkwy) | Construction of a new At-Grade 4-lane road | Road Extension | Both | Genito Road | Duval Road | Chesterfield | 232 | Project Regrouped | Regrouped Project Included in the constrained/Vision List
FHW-174 | 174 | VA-76 (Powhite Pkwy) | Construction of a new At-Grade 4-lane road | Road Extension | Both | Charter Colony Pkwy | Little Tomahawk Creek | Chesterfield | 240 | Project Regrouped | Regrouped Project Included in the constrained/Vision List